## Backlog
Sprint	User Type	Story ID	User Story	Tasks	Dependencies	Assignees		Story Points	Priority	Estimated-time	Actual-time	Duration (days)	Start Date	End Date
4	Instructor	4	US.04 - As an instructor, I want to be able to edit the teams once they have been made.	Task 12: Design a UI for instructors to edit teams	None	Kevin		2	Low	1 h	2 h	1	9-Nov	10-Nov
				Task 13: Create an API to add or remove students from teams	None	Owen				5 h	1 h 30 mn	1	11/24/2024	24-Nov
	Student	6	US.06 - As a student, I want to receive a notification when a peer assessment is available, / so that I don’t miss the opportunity to complete my evaluations	Task 16: Notification Box Implementation	None	Oussama		2	Low	1 h 30 mn	1 h	1	11/9/2024	11/9/2024
				Task 17: Notifying a peer that he or she hasn’t reviewed one or more team members	None	Aditi				1 h	2 h	4	6-Nov	10-Nov
	Instructor	7	US.07 - As an instructor, I want to export assessment results to a CSV file, so that I can analyze the data outside the platform if needed.	Task 18: Adding a button in both detailed and summary view pages for exporting to csv	None	Oussama		2	Low	1 h	30 mn	1	11/7/2024	11/7/2024
				Task 19: Being able to export to csv for detailed and summary view pages	None	Joyal				3 h	3 h 30 mn	1	11/23/2024	11/24/2024
	Student	9	US.09 - As a student I want to be able to chat with peers in my group	Task 23: Implement the layout (UI/UX) for the chatroom	None	Kevin		5	High	1 h	1 h 30 mn	1	7-Nov	7-Nov
				Task 24: Frontend for the chatroom - connection to database	Task 23	Jonathan				2 h	3 h	1	23-Nov	24-Nov
				Task 25: Database for the chatrooms	None	Jonathan				5 h	10 h	1	11/22/2024	11/24/2024
				Task 26: Implementation of chatbot to the chatroom	Tasks: 23 & 25	Jonathan				4 h	6 h 30 mn	2	11/22/2024	11/24/2024

Note: Since we completed most of the US for this sprint in sprint 3, we just added the ones that were uncomplete
Demo Video: https://drive.google.com/file/d/10i0J1ifvUp_IGe-xO8-wZjBgtgf7hqZv/view?usp=drive_link

## Duration
Duration
None
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## User_Type
User Type
None
Student
Instructor

## Assignee
Assignee
None
Aditi
Jonathan
Joyal
Kevin
Oussama
Owen

## Priority
Priority
None
Low (P0)
Medium
High

## Story_Points
Story Points (Fibonacci)
None
1
2
3
5
8
13

## Estimated-Time
Estimated Time
None
30 mn
1 h
1 h 30 mn
2 h
2 h 30 mn
3 h
3 h 30 mn
4 h
4 h 30 mn
5 h
5 h 30 mn
6 h
6 h 30 mn
7 h
7 h 30 mn
8 h
8 h 30 mn
9 h
9 h 30 mn
10 h