## Backlog
Sprint | User Type | Story ID | User Story | Tasks | Dependencies | Assignees | Story Points | Priority | Estimated-time | Actual-time | Duration (days) | Start Date | End Date
3 | Instructor | 1 | US.01 - As an instructor I want to be able to see the group peer assessments in a summary format | Task 01: Implement the layout (UI/UX) for the summary page | None | Joyal | 5 | High | 1 h 30 mn | 2 h 30 mn | 5 | 2024-11-05 | 2024-11-09
|  |  |  | Task 02: Implement a dashboard component to display assessment summaries | Task 01 | Joyal |  |  | 1 h | 1 h | 5 | 2024-11-05 | 2024-11-09
|  |  |  | Task 03: Develop the logic to fetch and display summary data from the backend | None | Owen |  |  | 1 h | 1 h | 1 | 2024-11-05 | 2024-11-06
|  |  |  | Task 04: Create an endpoint that calculates summary statistics for each team member’s ratings | Task 03 | Owen |  |  | 1 h | 1 h | 1 | 2024-11-05 | 2024-11-06
| Instructor | 2 | US.02 - As an instructor I want to be able to see the group peer assessments in a detailed format | Task 05: Implement the layout (UI/UX) for the detailed page | None | Joyal | 5 | High | 1 h 30 mn | 2 h 30 mn | 5 | 2024-11-05 | 2024-11-09
|  |  |  | Task 06: Implement a dashboard component to display detailed assessments | Task 05 | Joyal |  |  | 1 h | 1 h | 5 | 2024-11-05 | 2024-11-09
|  |  |  | Task 07: Develop the logic to fetch and display detailed data from the backend | None | Owen |  |  | 1 h 30 mn | 2 h | 2 | 2024-11-05 | 2024-11-07
|  |  |  | Task 08: Implement an endpoint that retrieves detailed assessment data by team or student | Task 07 | Owen |  |  | 1 h 30 mn | 2 h 30 mn | 2 | 2024-11-05 | 2024-11-07
| Student | 3 | US.03 - As a student, I want to add comments in each evaluation dimension, so that I can provide detailed feedback if desired | Task 09: Add text boxes for each dimension where students can enter comments on peer review page (UI/UX) | None | Oussama | 2 | Medium | 2 h | 1 h | 1 | 2024-11-08 | 2024-11-09
|  |  |  | Task 10: Display the text boxes for each dimension where students can view their comments for confirmation page (UI/UX) | Task 09 | Oussama |  |  | 1 h | 30 mn | 1 | 2024-11-07 | 2024-11-08
|  |  |  | Task 11: Update the database to store comments for each dimension | Task 10 | Owen |  |  | 2 h 30 mn | 2 h 30 mn | 1 | 2024-11-07 | 2024-11-08
| Instructor | 4 | US.04 - As an instructor, I want to be able to edit the teams once they have been made. | Task 12: Design a UI for instructors to edit teams | None | Kevin | 2 | Low | 1 h | 2 h | 1 | 2024-11-09 | 2024-11-10
|  |  |  | Task 13: Create an API to add or remove students from teams | None | Jonathan |  |  | 5 h | 1 h 30 mn | None | 2024-11-05 | None
| Instructor | 5 | US.05 - As an instructor, I want to see which students have completed their peer assessments, so that I can follow up with those who haven’t yet submitted. | Task 14: Create a view for instructors showing which students have completed assessments | None | Kevin | 5 | Low | 1 h 30 mn | 2 h 30 mn | 1 | 2024-11-09 | 2024-11-09
|  |  |  | Task 15: Develop the logic to fetch and display the data from the backend | None | Owen |  |  | 2 h 30 mn | 3 h | 1 | 2024-11-08 | 2024-11-09
| Student | 6 | US.06 - As a student, I want to receive a notification when a peer assessment is available, so that I don’t miss the opportunity to complete my evaluations | Task 16: Notification Box Implementation | None | Oussama | 2 | Low | None | None | None | None | None
|  |  |  | Task 17: Notifying a peer that he or she hasn’t reviewed one or more team members | None | Aditi |  |  | 1 h | 2 h | None | 2024-11-06 | 2024-11-10
| Instructor | 7 | US.07 - As an instructor, I want to export assessment results to a CSV file, so that I can analyze the data outside the platform if needed. | Task 18: Adding a button in both detailed and summary view pages for exporting to csv | None | Oussama | 2 | Low | None | None | 1 | None | None
|  |  |  | Task 19: Being able to export to csv for detailed and summary view pages | None | Jonathan |  |  | 3 h | 1 h 30 mn | 1 | 2024-11-05 | None
| Instructor | 8 | US.08 - As an instructor I want to be able to see a page to view reviews | Task 20: Implement the layout (UI/UX) for the "Peer assessment" page. | None | Oussama | 2 | High | 1 h 30 mn | 1 h | 2 | 2024-11-08 | 2024-11-10
|  |  |  | Task 21: Add 3 buttons: one directed to the detailed review page, summary review page, one to completion page | None | Oussama |  |  | 1 h | 30 mn | 1 | 2024-11-09 | 2024-11-10
|  |  |  | Task 22: Set up routing for the “Peer Assessement” page | None | Oussama |  |  | 1 h | 30 mn | 1 | 2024-11-09 | 2024-11-10
| Student | 9 | US.09 - As a student I want to be able to chat with peers in my group | Task 23: Implement the layout (UI/UX) for the chatroom | None | Kevin | 5 | High | 1 h | 1 h 30 mn | 1 | 2024-11-07 | 2024-11-07
|  |  |  | Task 24: Frontend for the chatroom - connection to database | Task 23 | Aditi |  |  | None | None | None | None | None
|  |  |  | Task 25: Database for the chatrooms | None | Jonathan |  |  | 1 h | 30 mn | 1 | 2024-11-03 | 2024-11-03
|  |  |  | Task 26: Implementation of chatbot to the chatroom | Tasks: 23 & 25 | Jonathan |  |  | 5 h | 10 h | 2 | 2024-11-09 | 2024-11-10

## Duration
Duration
None
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## User Type
User Type
None
Student
Instructor

## Assignee
Assignee
None
Aditi
Jonathan
Joyal
Kevin
Oussama
Owen

## Priority
Priority
None
Low (P0)
Medium
High

## Story Points
Story Points (Fibonacci)
None
1
2
3
5
8
13

## Estimated-Time
Estimated Time
None
30 mn
1 h
1 h 30 mn
2 h
2 h 30 mn
3 h
3 h 30 mn
4 h
4 h 30 mn
5 h
5 h 30 mn
6 h
6 h 30 mn
7 h
7 h 30 mn
8 h
8 h 30 mn
9 h
9 h 30 mn
10 h