## Sheet1
Sprint | User Type | Story ID | User Story | Tasks | Assignees |  | Story Points | Priority | Estimate-time
2 | Student | 1 | Click the Peer Assessment Button | UI/UX for button on the student dashboard | Joyal |  | 3 | Low | 30 minutes
|  |  |  | Route for peer selection page | Jonathan |  |  |  | 5-6 hours
| Student | 2 | Type the Name of a Peer | UI/UX for search button with dropdown | Kevin |  | 1 | Low | 1 hour
|  |  |  | Connection to the Users Table | Aditi |  |  |  | 3-4 hours
| Student | 3 | View Peer List in a Dropdown | Frontend for looping peer names | Aditi |  | 5 | Medium | 2 hours
|  |  |  | Backend to fetch peer list from the Users Table | Jonathan |  |  |  | 2 hours
| Student | 4 | Navigate to Peer Evaluation Page | UX/UI for the "Review Peer" button | Kevin |  | 2 | High | 2 hours
|  |  |  | Backend for routing to the evaluation page | Jonathan |  |  |  | 3-4 hours
| Student | 5 | Evaluate Peer Based on Dimensions and Submit Review | UI/UX for the evaluation form | Joyal |  | 8 | High | 3 hours
|  |  |  | Frontend to post the evaluation data | Oussama |  |  |  | 2 hours
|  |  |  | Backend to store evaluation data in the table | Owen |  |  |  | 3-4 hours
|  |  |  | Frontend validation for required fields | Joyal |  |  |  | 2 hours
|  |  |  | User-friendly feedback for incomplete forms | Joyal |  |  |  | 30 minutes
|  |  |  | Responsive design and layout | Joyal |  |  |  | 30 minutes
|  |  |  | Form styling and theming | Joyal |  |  |  | 30 minutes
|  |  |  | Interactive star rating system for each dimension | Oussama | Joyal |  |  | 1 hour
| Student | 6 | Confirm Peer Review Submission | UI/UX for the confirmation page | Oussama | Joyal | 8 | High | 1 jour
|  |  |  | Frontend for viewing the review | Oussama |  |  |  | 1 hour
|  |  |  | Backend for collecting reviews from the evaluation table | Jonathan |  |  |  | 2 hours
|  |  |  | Add Confirmation Modal Before Final Submission | Oussama |  |  |  | 1 hour
|  |  |  | Add Dynamic Feedback Summary on Thank-You Page | Oussama | Joyal |  |  | 30 minutes
|  |  |  | UI/UX for thank you page | Oussama | Joyal |  |  | 2 hours
| Student | 7 | Cancel a Peer Review | UI/UX for the cancel button | Oussama |  | 2 | Medium | 30 minutes
|  |  |  | Backend to delete peer data from the evaluation table | Owen |  |  |  | 2 hours
| Student | 8 | View Peer Reviews | UI/UX for the "View Reviews" button and page | Kevin |  | 1 | Medium | 2 hours
|  |  |  | Backend to fetch reviews for the selected peer | Aditi |  |  |  | 3 hours
| Student | 9 | View List of Peer Reviews | Backend for fetching evaluation data from the evaluation table | Owen |  | 5 | Medium | 2 hours
|  |  |  | Frontend to display the evaluations | Owen |  |  |  | 1 hour